Calvert County, Maryland

Local Drug and Alcohol Council

Strategic Plan Update

January, 2009

Goal 1:	Continue to educate the citizens of Calvert County about substance use and abuse among its citizens and the negative effects upon family and community life.

Objective I	Increase efforts in public awareness campaigns that reach all Calvert residents and are supported by multiple county agencies.

Action Steps

- Increase the number of evidence based prevention programs offered during the year.

Progress:	Program offerings continue to increase.  Projection at this point is for a 60% increase in the number of “Guiding Good Choices” Programs offered during FY 2009

- To increase referrals, conduct a series of meetings with social service organizations, schools, civic groups, treatment providers and criminal/juvenile justice agencies regarding available programming in the County

Progress:	Meetings being held on an on-going basis

- Secure additional funding for prevention efforts

Progress:	No additional funding is secured at this time.

- Do newspaper articles in local papers

Progress:	Articles have been written although not necessarily for the newspaper

Measurable Output

- Increase the number of participants in prevention programs by 10%

UPDATE:	In FY 2008, Calvert Substance Abuse Services’ Prevention Program provided services to 5,124 citizens which represented a 244% increase from the year before.  Thus far in FY 2009, 6,127 citizens have been served which projects to a 239% increase for this Fiscal Year.  The county’s other prevention agency, Calvert Alliance Against Substance Abuse, also sponsors many events during the year.  Information regarding those events was not available as of the time of this writing.

Objective 2	Create a formal mechanism through which all prevention agencies, providers and other groups coordinate activities

Action Steps

- Present “Network of Care” software program to county/local state agencies, social service organizations, treatment and prevention providers, criminal/juvenile justice agencies

Progress:	Completed

- Train parties in use of program and prepare web-site

Progress:	Website prepared, training being conducted currently

- Make web-site available to public, which will greatly ease any citizen’s ability to access appropriate programs

Progress:	Web-site is fully operational

Goal 2:	Maintain the current continuum of treatment services accessible by County residents while adding affordable access to buprenorphine treatment (potentially subsidizing treatment for qualified citizens).

Objective I	Recruit doctor(s) licensed to provide buprenorphine treatment and willing to contract for referrals

Action Steps

- Determine what (if any) County doctors are licensed to treat with buprenorphine

Progress:	Completed

- Meet with doctors to determine costs

Progress:	Completed

- Secure funding to meet County need for buprenorphine treatment

Progress:	Granted $9240 by the Alcohol and Drug Abuse Administration

- Contract with doctors

Progress:	Completed

Objective 2	Determine the potential population in need of financially assisted buprenorphine treatment

Action Steps

- Review available statistics from ADAA

Progress:	Completed

- Review available statistics from Calvert Substance Abuse Services

Progress:	Completed

- Establish income-assistance qualifications

Progress:	Completed

UPDATE:	2 clients have used buprenorphine funding to date

Goal 3:	Increase the accountability of outpatient treatment clients

Objective I	Increase the number of drug tests conducted on clients

Action Steps

- Secure additional funding for tests

Progress:	No additional funding secured

- Develop schedule for increased testing relating such schedule to treatment level of care (the higher the level of treatment, the more tests conducted)

Progress:	Schedule has been adopted

Measurable Output

- Increase the number of tests conducted by 10%

Actual Output

- Number of tests conducted actually remained the same for FY 2008 as FY 2007 but with a slight decline in the number of patients.  Thus far in FY 2009, the number of tests completed projects to a 7.6% annual increase.

Objective 2	Increase test-related fee collections

Action Steps

- Have all counselors emphasize to clients the need for prompt payment of bills.

Progress:	Completed

- Billings will be prompt and verbiage on bills should be “strongly” worded.

Progress:	Completed

- Reporting to referring source any payment delinquencies

Progress:	Current and Ongoing

Measurable Output

- Increase in fees collected

- Corresponding decrease in bad debt

Actual Output

- Fee collections rose by 24.7% during FY 2008 (compared to FY 2007).  Thus far in FY 2009 collections project to a 5.2% increase from FY 2008.

Goal 4:	Provide the Emergency Psychiatric Services (EPS) staff of Calvert Memorial Hospital a 			viable option for substance abusing clients (who are in the emergency room) in need of

medically supervised detoxification

Objective I	Establish agreements for services

Action Steps

- Secure additional funding

Progress:	No funding

- Contract with transportation carrier to ensure bed to bed coverage

Progress:	Contingent on funding – See Action Step 1

- Contract with Level III.7D residential facility to have bed available on daily basis

Progress:	Contingent on funding – See Action Step 1

- Contract with hospital

Progress:	Contingent on funding – See Action Step 1

Objective 2	Develop procedures for referrals

Action Steps

- Have EPS staff trained in the use of ASAM criteria

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

- Develop memoranda of understanding

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

- Establish procedures for billings and payments

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

Objective 3	Have appropriate clients go directly from Calvert Memorial Hospital to Anchor of St. Mary’s County

Action Steps

- Emergency room screening of EPS clients by hospital staff

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

- Referral to Anchor of St. Mary’s County

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

- Coordinate transportation of clients to Anchor of St. Mary’s County

Progress:	Contingent on funding –

See Goal 4, Objective 1, Action Step 1

Goal 5:	Enhance the system of substance abuse prevention, intervention and treatment services for Calvert County adolescents

Objective I	Support the Calvert County Juvenile Drug Court

Action Steps

- Hold meetings with all participating agencies

Progress:	Completed

- Reconsider qualifications for court participation

Progress:	Completed

- Increase participants in Juvenile Drug Court

Progress:	Number of participants rose from 4 in FY 2007 to 15 in FY 2008.  This represents a 375% increase.  Thus far in FY 2009, there have been 15 participants which would project to a 100% annual increase.

Objective 2	Better utilization of substance abuse treatment services in the secondary schools

Action Steps

- Meetings between the Board of Education staff and the Substance Abuse Services staff

Progress:	Completed

- Individual meetings between secondary school principals and Substance Abuse program director

Progress:	Completed

- Quarterly progress/adjustment meetings between Board of Education Staff and Substance Abuse Services Staff

Progress:	Ongoing

Goal 6:	Maintain complete and full collaboration among community entities (primary and secondary) that serve substance abusers

Objective I	Annual cross trainings among all community agencies

Action Steps

- Schedule Meeting(s)

Progress:	Completed and ongoing

- Notify potential participants and gather agenda items

Progress:	Completed and ongoing

- Conduct meeting(s)

Progress:	Completed and ongoing

- Provide notes to all involved agencies

Progress:	Completed and ongoing

Objective 2	Maintain interagency coalition

Action Steps

- Meetings of Local Drug and Alcohol Abuse Council

Progress:	Completed and ongoing

- Agency sharing of pertinent data

Progress:	Completed and ongoing

- Discussion/development of potential new programs and/or resources

Progress:	Completed and ongoing