Goal 1:	Continue to educate the citizens of Calvert County about substance use and abuse among its citizens and the negative effects upon family and community life.

Objective I	Increase efforts in public awareness campaigns that reach all Calvert residents and are supported by multiple county agencies.

- Action Steps

- Increase the number of evidence based prevention programs offered during the year.

Progress:		Number of programs offered is increasing

- To increase referrals, conduct a series of meetings with social service organizations, schools, civic groups, treatment providers and criminal/juvenile justice agencies regarding available programming in the County

Progress:	Meetings have been held or are scheduled with county social service organizations

- Secure additional funding for prevention efforts

Progress:	Two grant applications have been made.  One was rejected, one as yet to be determined.

- Do newspaper articles in local papers

Progress:		Not yet completed

Objective 2	Create a formal mechanism through which all prevention agencies, providers and other groups coordinate activities

Action Steps

- Present “Network of Care” software program to county/local state agencies, social  service organizations, treatment and prevention providers, criminal/juvenile justice agencies

Progress:		Presentation has been made

- Train parties in use of program and prepare web-site

Progress:		Training to be conducted

- Make web-site available to public, which will greatly ease any citizen’s ability to access appropriate programs

Progress:		Web site not yet available

Goal 2:	Maintain the current continuum of treatment services accessible by County residents while adding affordable access to buprenorphine treatment (potentially subsidizing treatment for qualified citizens).

Objective I	Recruit doctor (s) licensed for buprenorphine treatment and willing to contract for referrals

Action Steps

- Determine what (if any) County doctors are licensed to treat with buprenorphine

Progress:		Doctor has been identified

- Meet with doctors to determine costs

Progress:		Meeting has been held

- Secure funding to meet County need for buprenorphine treatment

Progress:	No additional information on funding from the Alcohol and Drug Abuse Administration (ADAA)

- Contract with doctors

Progress:		Dependant on funding

Objective 2	Determine the potential population in need of financially assisted buprenorphine treatment

Action Steps

- Review available statistics from ADAA

Progress:		Completed

- Review available statistics from Calvert Substance Abuse Services

Progress:		Completed

- Establish income-assistance qualifications

Progress:		Completed

Goal 3:	Increase the accountability of outpatient treatment clients

Objective I	Increase the number of drug tests conducted on clients

Action Steps

- Secure additional funding for tests

Progress:		No additional funding has been secured

- Develop schedule for increased testing relating such schedule to treatment level of care (the higher the level of treatment, the more tests conducted)

Progress:		Schedule has been adopted

Measurable Output

- Increase the number of tests conducted by 10%

Actual Output

- Number of tests conducted has risen by about 8% (through November, 2007)

Responsibility:	Calvert Substance Abuse Services, Redwood Labs (California)

Objective 2	Increase test-related fee collections

Action Steps

- Have all counselors emphasize to clients the need for prompt payment of bills.

Progress:		Completed

- Billings will be prompt and verbiage on bills should be “strongly” worded.

Progress:		Completed

- Reporting to referring source any payment delinquencies

Progress:		Ongoing

Measurable Output

- Increase in fees collected

- Corresponding decrease in bad debt

Actual Output

- Fees collected through November project to a 41% increase for FY 2008.  This has occurred despite no additional fundings.

Goal 4:	Provide the Emergency Psychiatric Services (EPS) staff of Calvert Memorial Hospital a viable option for substance abusing clients (who are in the emergency room) in need of medically supervised detoxification

Objective I	Establish agreements for services

Action Steps

- Secure additional funding

Progress:		No funding secured

- Contract with transportation carrier to ensure bed to bed coverage

Progress:		Contingent on funding

- Contract with Level III.7D residential facility to have bed available on daily basis

Progress:		Contingent on funding

- Contract with hospital

Progress:		Contingent on funding

Objective 2	Develop procedures for referrals

Action Steps

- Have EPS staff trained in the use of ASAM criteria

Progress:		Will be attempted after funding received

- Develop various memoranda of understanding

Progress:	Meetings have been held but no agreements necessary unless program needed

- Establish procedures for billings and payments

Progress:		No need as yet

Objective 3	Have appropriate clients go directly from Calvert Memorial Hospital to Anchor of St. Mary’s County

Action Steps

- Emergency room screening of EPS clients by hospital staff

Progress:		Plan not in operation

- Referral to Anchor of St. Mary’s County

Progress:		Plan not in operation

- Coordinate transportation of clients to Anchor of St. Mary’s County

Progress:		Plan not in operation

Goal 5:	Enhance the system of substance abuse prevention, intervention and treatment services for Calvert County adolescents

Objective I	Support the Calvert County Juvenile Drug Court

Action Steps

- Hold meetings with all participating agencies

Progress:		Completed

- Reconsider qualifications for court participation

Progress:		Completed

- Increase participants in Juvenile Drug Court

Progress:	Number of participants appears to be steadily increasing

Objective 2	Better utilization of substance abuse treatment services in the secondary schools

Action Steps

- Back to school meetings between the Board of Education staff and Substance Abuse Services staff

Progress:		Completed

- Individual meetings between secondary school principals and Substance Abuse program director

Progress:		Semi-completed

- Quarterly progress/adjustment meetings between Board of Education Staff and Substance Abuse Services Staff

Progress:		Ongoing

Goal 6:	Maintain complete and full collaboration among community entities (primary and secondary) that serve substance abusers

Objective I	Annual cross trainings among all community agencies

Action Steps

- Schedule Meeting

Progress:		No meeting scheduled

- Notify potential participants and gather agenda items

Progress:		No meeting scheduled

- Conduct meetings

Progress:		No meeting scheduled

- Provide notes to all involved agencies

Progress:		No meeting scheduled

Objective 2	Maintain interagency coalition

Action Steps

- Quarterly meetings of Local Drug and Alcohol Abuse Council

Progress:		On schedule for late January, 2008

- Agency sharing of pertinent data

Progress:	Will occur at quarterly meeting but is also taking place on a daily basis throughout the county

- Discussion/development of potential new programs and/or resources

Progress:		Will occur officially during FY 2009 Grant writing and review but, this also occurs on a daily basis throughout the county.  This is particularly true of prevention efforts throughout Calvert County.